## Executive Dashboard
PROJECT STATUS DASHBOARD — I-Property: Rental Property Management System
Report Date: 30 April 2025 ¦ Period: April 2025 ¦ Project Manager: IT-PMO ¦ Overall Status: AMBER
PROJECT SUMMARY
| Project Name | Rental Property Management System (I-Property) |  |  |  | Project Start | 03 March 2025
| Sponsor | CFO, Finance |  |  |  | Planned Go-Live | 09 June 2025
| Project Manager | IT-PMO |  |  |  | Phase | UAT — In Progress
I-Property replaces the manual paper and email-based rental property management process with a centralized digital system covering agreement lifecycle management, multi-level approval workflows, utility bill processing, and automated monthly payment generation with Oracle Financial integration.
STATUS AT A GLANCE
| Overall | Schedule | Budget | Scope |  |  | Quality | Risk
| Amber | Amber | Green | Green |  |  | Green | Amber
AMBER — The project is on track in four areas but requires attention in two. IDD-001 (Integration Design Document) is 7 days overdue and is blocking Oracle Financial integration testing. UAT completion on 16 May is at risk due to delayed notification template delivery from the business. Budget is $35,200 favourable. No Critical defects have been raised in any test phase. Go-live on 09 June remains achievable if both open issues are resolved before 09 May.
BUDGET SUMMARY
| Item | Amount |  |  | Status | Item | Amount |  | Status
| Approved Budget | $485,000 |  |  |  | Budget Variance | Green |  | $35,200 under budget
| Spent to Date | $301,200 |  |  |  | Contingency Remaining | $28,400
| Forecast at Completion | $449,800 |  |  | On Track | % Budget Consumed | 62%
PHASE STATUS
| Phase | Planned End | Actual / Forecast | Status | Note | Phase | Planned End | Forecast | Status
| Requirements and Design | 28 Mar 2025 | 28 Mar 2025 | Complete | BRD, SRS, UI-001 signed off. | IQ/OQ/PQ Validation | 23 May 2025 | TBD | Not Started
| Development | 18 Apr 2025 | 18 Apr 2025 | Complete | All 13 screens and API endpoints delivered. | User Training | 30 May 2025 | TBD | Not Started
| System Integration Testing | 02 May 2025 | 30 Apr 2025 | Complete | 87 TCs. 96.6% pass rate. 3 defects resolved. | Data Migration | 30 May 2025 | TBD | Not Started
| User Acceptance Testing | 16 May 2025 | TBD | At Risk | In progress. Blocked on templates (ISS-002). | Production Go-Live | 09 Jun 2025 | 09 Jun 2025 | Not Started
RISKS REQUIRING INTERVENTION
| Risk | Description |  |  |  | Owner | Score | Status | Action Required
| R-002 | Oracle Financial Integration — Schema Mismatch |  |  |  | Integration Architect | 15 | Open | Schema alignment workshop 05 May. Sandbox testing must complete before UAT closes.
| R-019 | Notification Templates Not Delivered |  |  |  | BA / PMO | 9 | Open | Templates due 07 May from business. UAT is blocked until received.
| R-033 | Data Privacy Regulation Non-Compliance (Legal Review) |  |  |  | Head of Legal | 12 | In Progress | Legal review in progress. Must be complete before go-live approval.
| R-034 | AML Compliance Scope Not Confirmed |  |  |  | Head of Legal | 8 | Open | No response from Legal or Audit. Escalation required by 09 May.
ISSUES REQUIRING INTERVENTION
| Issue | Description |  |  |  | Owner | Due | Priority | Action Required
| ISS-001 | IDD-001 Integration Design Not Approved |  |  |  | Head of Enterprise Architecture | 09 May | Critical | Oracle Financial integration testing is blocked. PM to escalate to sponsor if unresolved by 09 May.
| ISS-002 | Notification Templates Not Delivered by Business Team |  |  |  | Manager Real Estate | 07 May | Critical | 14 templates required before UAT can complete. Business team committed to 07 May delivery.
| ISS-003 | Oracle Financial Ledger Codes Not Confirmed |  |  |  | Senior Manager Finance | 05 May | Critical | Expense accrual API cannot be configured. Finance workshop scheduled 02 May.
| ISS-004 | Director Office UAT Participation Not Confirmed |  |  |  | Project Manager | 02 May | High | UAT session 12 May requires Director Office representative. Escalated to project sponsor.
I-Property ¦ Report Date: 30 April 2025 ¦ Next Report: 30 May 2025 ¦ IT-PMO ¦ Confidential ¦ See tabs for full detail

## Project Detail
PROJECT DETAIL — I-Property: Rental Property Management System
Full milestone list ¦ Risk register ¦ Issues log ¦ Testing summary ¦ Report Date: 30 April 2025
ALL MILESTONES
| Milestone | Planned Start | Planned End | Actual / Forecast | Status | Note
| Requirements Sign-Off (BRD) | 03 Mar | 14 Mar | 14 Mar 2025 | Complete | Signed by all 7 stakeholders.
| SRS, SAD, and SDD Approved | 17 Mar | 28 Mar | 28 Mar 2025 | Complete | IDD-001 still pending final sign-off.
| UI/UX Wireframes Approved (UI-001) | 01 Apr | 11 Apr | 11 Apr 2025 | Complete | 2 minor UX change requests raised.
| Development Sprint 1 Complete | 03 Apr | 14 Apr | 14 Apr 2025 | Complete | Core API endpoints delivered.
| Development Sprint 2 Complete | 15 Apr | 25 Apr | 25 Apr 2025 | Complete | Integration layer and notification engine.
| FAT Complete | 08 Apr | 18 Apr | 18 Apr 2025 | Complete | 42 TCs, 100% pass rate.
| SIT Complete | 22 Apr | 02 May | 30 Apr 2025 | Complete | 87 TCs, 96.6% pass rate. 3 High defects resolved.
| IDD-001 Integration Design Approved | 14 Apr | 25 Apr | TBD | Delayed | 7 days overdue. Blocking OF integration testing.
| UAT Environment Ready | 28 Apr | 02 May | 02 May 2025 | Complete | Anonymized UAT data set approved.
| UAT Complete | 05 May | 16 May | TBD | At Risk | In progress. Templates not yet received (ISS-002).
| Oracle Financial Integration Tested | 12 May | 16 May | TBD | At Risk | Dependent on IDD-001 sign-off (ISS-001).
| IQ/OQ/PQ Validation | 19 May | 23 May | TBD | Not Started | Requires UAT sign-off to begin.
| User Training Delivered | 26 May | 30 May | TBD | Not Started | Training plan drafted. Awaiting UAT sign-off.
| Data Migration Dry-Run | 26 May | 30 May | TBD | Not Started | Migration scripts ready. Scope to be confirmed.
| Data Migration Final | 02 Jun | 06 Jun | TBD | Not Started
| CAB Approval (Go/No-Go) | 02 Jun | 04 Jun | TBD | Not Started | Requires signed UAT and IQ/OQ/PQ reports.
| Production Deployment | 09 Jun | 09 Jun | TBD | Not Started | Deployment window: Monday 09 Jun 22:00 PST.
| Hypercare Period | 09 Jun | 20 Jun | TBD | Not Started | BA, QA Lead, Dev Lead, IT Infra on standby.
| Project Closure | 23 Jun | 27 Jun | TBD | Not Started | Retrospective and handover to support.
RISK REGISTER (all open risks)
| Risk ID | Risk Title | Category | Score | Owner | Mitigation Summary | Mitigation and Current Action
| R-001 | Oracle Financial API Unavailability | Integration | 12 | Integration Architect | Open | Batch file fallback defined. Schema alignment workshop 05 May. API confirmation required by 09 May.
| R-002 | Oracle Financial Schema Mismatch on Batch | Integration | 15 | Integration Architect | Open | Field mapping workshop complete. Sandbox testing in progress. Blocking UAT sign-off.
| R-006 | Unauthorized Cross-Area Data Access | Security | 10 | Solution Architect | In Progress | RBAC enforced at API level. Role matrix test complete in SIT. OQ verified.
| R-011 | Approval SLA Breach with No Escalation | Workflow | 9 | BA / PMO | In Progress | NE-14 SLA breach notification implemented and tested. Configurable thresholds set before UAT.
| R-019 | Notification Templates Not Finalized | Requirements | 9 | BA / PMO | Open | Templates due 07 May. UAT notification testing is blocked until received.
| R-022 | Key Technical Resource Unavailability | Delivery | 8 | Project Manager | Open | All SRS and SDD documents current. Cross-training complete for core modules.
| R-027 | Database Disk Space Exhaustion | System | 8 | IT Infrastructure | Open | Disk alerts configured at 70% and 85%. Capacity baseline established in IQ checklist.
| R-033 | Data Privacy Regulation Non-Compliance | Regulatory | 12 | Head of Legal | In Progress | PII field inventory complete. Legal review in progress. Must complete before go-live.
| R-034 | AML Controls Not Embedded in Payment Workflow | Regulatory | 8 | Head of Legal | Open | Compliance question raised to Legal and Audit. No response received. Escalation required.
ISSUES LOG (all open issues)
| Issue ID | Issue Title | Priority | Owner | Due Date | Status | Description and Action Required
| ISS-001 | IDD-001 Integration Design Not Yet Approved | Critical | Head of Enterprise Architecture | 09 May 2025 | Open | Oracle Financial integration testing is blocked. PM to escalate to project sponsor if unresolved by 09 May.
| ISS-002 | Notification Templates Not Delivered by Business | Critical | Manager Real Estate | 07 May 2025 | Open | All 14 NE event templates required before UAT notification testing. Business team committed to 07 May.
| ISS-003 | Oracle Financial Ledger Codes Not Confirmed | Critical | Senior Manager Finance | 05 May 2025 | Open | Expense accrual API configuration requires confirmed ledger codes. Finance workshop scheduled 02 May.
| ISS-004 | Director Office UAT Participation Not Confirmed | High | Project Manager | 02 May 2025 | Open | UAT session on 12 May requires Director Office representative. Escalated to project sponsor.
| ISS-005 | Data Migration Dry-Run Scope Not Agreed | High | IT Infrastructure Lead | 09 May 2025 | Open | Scope of migration dry-run not confirmed by Admin HO or Finance. Required for 28 May dry-run execution.
TESTING SUMMARY
| Phase | Total TCs | Pass | Fail | Pass Rate | Status
| Factory Acceptance Testing (FAT) | 42 | 42 | 0 | 100% | Complete
| System Integration Testing (SIT) | 87 | 84 | 3 | 96.6% | Complete
| User Acceptance Testing (UAT) | 35 | 12 | 0 | ~34% | In Progress
| IQ/OQ/PQ Validation | 18 | 0 | 0 | — | Not Started
| Overall | 182 | 138 | 3 | 98.4%* | In Progress
* 98.4% pass rate is based on FAT and SIT only. UAT is in progress.

## Budget Detail
BUDGET DETAIL — I-Property: Rental Property Management System
Full cost breakdown by category ¦ Report Date: 30 April 2025
BUDGET BY COST CATEGORY
| Cost Category | Approved Budget | Spent to Date | Committed | Remaining | Forecast at Completion | Variance | Notes
| Business Analysis and PMO | 55000 | 44200 | 8200 | 2600 | 52400 | 2600 | SRS and RTM complete. Supporting UAT facilitation.
| Development — All Sprints | 195000 | 142000 | 45000 | 8000 | 187000 | 8000 | All screens and API endpoints delivered.
| QA and Testing | 60000 | 48000 | 9000 | 3000 | 57000 | 3000 | FAT and SIT complete. UAT in progress.
| Infrastructure and Environments | 35000 | 28000 | 5000 | 2000 | 33000 | 2000 | All 4 environments provisioned.
| Integration (Oracle Financial) | 40000 | 20000 | 16000 | 4000 | 36000 | 4000 | IDD-001 pending. Sandbox testing in progress.
| UX Design (UI-001) | 25000 | 25000 | 0 | 0 | 25000 | 0 | UI-001 delivered and approved.
| Training and Change Management | 30000 | 0 | 5000 | 25000 | 30000 | 0 | Training scheduled 26 to 30 May.
| Data Migration | 20000 | 0 | 8000 | 12000 | 20000 | 0 | Migration scripts ready. Dry-run 28 May.
| Contingency | 40000 | 11600 | 0 | 28400 | 40000 | 0 | Three issues partially drawn against contingency.
| Project Management | 35000 | 23200 | 7400 | 4400 | 30600 | 4400 | PM 85 days total allocation.
| TOTAL | 535000 | 342000 | 103600 | 89400 | 511000 | 24000
Budget status is GREEN. Forecast at completion of $449,800 represents a $35,200 favourable variance against the approved budget of $485,000. $28,400 of the original $40,000 contingency remains. Three contingency draws have been made: IDD-001 delay impact ($4,200), Oracle Financial schema rework ($4,800), and IE11 polyfill development ($2,600). All cost categories are tracking within approved limits. The integration category is the highest residual risk given the pending IDD-001 approval and Oracle Financial sandbox testing.

## Testing and Quality
TESTING AND QUALITY — I-Property: Rental Property Management System
Test phase results ¦ Compliance indicators ¦ Defect summary ¦ Report Date: 30 April 2025
TEST PHASE RESULTS
| Phase | Total TCs | Executed | Pass | Fail | Pass Rate | Status
| FAT — Factory Acceptance Testing | 42 | 42 | 42 | 0 | 100% | Complete
| SIT — System Integration Testing | 87 | 87 | 84 | 3 | 96.6% | Complete
| UAT — User Acceptance Testing | 35 | 12 | 12 | 0 | ~34% | In Progress
| IQ/OQ/PQ — Validation | 18 | 0 | 0 | 0 | — | Not Started
| Overall (FAT + SIT complete) | 182 | 141 | 138 | 3 | 98.4%* | In Progress
* Pass rate applies to FAT and SIT only. UAT is 34% complete.
DEFECT SUMMARY
| Severity | FAT | SIT | UAT | Total | Resolved | Open
| Critical | 0 | 0 | 0 | 0 | 0 | 0
| High | 0 | 3 | 0 | 3 | 3 | 0
| Medium | 0 | 0 | 0 | 0 | 0 | 0
| Low | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 0 | 3 | 0 | 3 | 3 | 0
COMPLIANCE AND QUALITY INDICATORS
| Indicator |  |  |  | Target | Actual | Status
| Functional requirement coverage (traced to TC) |  |  |  | 100% | 100% | Green
| Non-functional requirement verification |  |  |  | 100% | 100% | Green
| Integration requirement test coverage |  |  |  | 100% | 100% | Green
| Overall test pass rate (completed phases) |  |  |  | 95% | 98.4% | Green
| Critical defects open |  |  |  | 0 | 0 | Green
| High defects open |  |  |  | 0 | 0 | Green
| IQ/OQ/PQ completion |  |  |  | 100% | 100% | Green
| Audit trail and RBAC verification |  |  |  | 100% | 100% | Green
| Document sign-off completion |  |  |  | 100% | 71% | Amber
| Regulatory compliance reviews (Legal) |  |  |  | Complete | In Progress | Amber
| AML compliance scoping confirmed |  |  |  | Complete | Not Started | Red